Spatial Estimation of Surface Urban Heat Island Intensity in Davao City

Thesis Chapters 1–3 Gantt Chart

24 August – 15 November

■ Writing    ■ Research / preparation    ■ Consultation / review    ■ Revision / integration    ■ Presentation / milestone

| PHASE | ACTIVITY | Aug 24–30 | Aug 31– Sep 6 | Sep 7–13 | Sep 14–20 | Sep 21–27 | Sep 28– Oct 4 | Oct 5–11 | Oct 12–18 | Oct 19–25 | Oct 26– Nov 1 | Nov 2–8 | Nov 9–15 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CH 1 | Core drafting |  |  |  |  |  |  |  |  |  |  |  |  |
| CH 1 | Internal review & adviser consultation |  |  | ● |  |  |  |  |  |  |  |  |  |
| CH 1 | Revision & chapter freeze |  |  |  | ● |  |  |  |  |  |  |  |  |
| CH 2 | Literature search, screening & evidence map |  |  |  |  |  |  |  |  |  |  |  |  |
| CH 2 | Synthesis, conceptual framework & drafting |  |  |  |  |  |  |  |  |  |  |  |  |
| CH 2 | Consultations & targeted revision |  |  |  |  |  | ● |  |  |  |  |  |  |
| CH 2 | Finalization and reference audit |  |  |  |  |  |  | ● |  |  |  |  |  |
| CH 3 | Method design & data feasibility check |  |  |  |  |  |  |  |  |  |  |  |  |
| CH 3 | Methodology drafting |  |  |  |  |  |  |  |  |  |  |  |  |
| CH 3 | Consultation / internal presentation |  |  |  |  |  |  |  |  | ● |  |  |  |
| CH 3 | Revision, integration & adviser clearance |  |  |  |  |  |  |  |  |  | ● |  |  |
| FULL | Slides, speaking roles & mock defense |  |  |  |  |  |  |  |  |  |  |  |  |
| FULL | Final proposal presentation / defense |  |  |  |  |  |  |  |  |  |  | ● |  |
| FULL | Post-presentation corrections / contingency |  |  |  |  |  |  |  |  |  |  |  | ● |

Second-Semester Gantt Chart

January – May 2027

■ Writing   ■ Research / preparation   ■ Methodology / data   ■ Consultation / review   ■ Revision / integration   ■ Presentation / milestone

| PHASE | ACTIVITY | JAN W1 | JAN W2 | JAN W3 | JAN W4 | FEB W1 | FEB W2 | FEB W3 | FEB W4 | MAR W1 | MAR W2 | MAR W3 | MAR W4 | APR W1 | APR W2 | APR W3–4 | MAY |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SETUP | Outline corrections, protocol freeze & task ownership |  | ● |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DATA | Satellite, OSM road and boundary data inventory / download |  |  |  | ● |  |  |  |  |  |  |  |  |  |  |  |  |
| DATA | Satellite calibration, QA masking and spatial alignment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAPH | OSM road cleaning, intersection consolidation and graph audit |  |  |  |  |  | ● |  |  |  |  |  |  |  |  |  |  |
| FEATURE | LST/SUHI, NDVI, NDBI and road-feature extraction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FEATURE | Node integration, buffer checks and attributed graph freeze |  |  |  |  |  |  | ● |  |  |  |  |  |  |  |  |  |
| DESIGN | Spatial/temporal splits, leakage checks and evaluation freeze |  |  |  |  |  |  | ● |  |  |  |  |  |  |  |  |  |
| MODEL | Random Forest baseline training and tuning |  |  |  |  |  |  |  |  | ● |  |  |  |  |  |  |  |
| MODEL | Spatial GCN training, tuning and topology ablations |  |  |  |  |  |  |  |  |  | ● |  |  |  |  |  |  |
| OUTPUT | Project output / dashboard build and testing |  |  |  |  |  |  |  |  |  |  | ● |  |  |  |  |  |
| RESULTS | RMSE, MAE, R², residual analysis and SUHI mapping |  |  |  |  |  |  |  |  |  |  | ● |  |  |  |  |  |
| WRITE | Chapters 4–5 and full manuscript integration |  |  |  |  |  |  |  |  |  |  |  | ● |  |  |  |  |
| REVIEW | Adviser review, action report closure and endorsement |  |  |  |  |  |  |  |  |  |  |  |  | ● |  |  |  |
| DEFENSE | Panel copies, slides, speaking roles and mock defense |  |  |  |  |  |  |  |  |  |  |  |  | ● |  |  |  |
| DEFENSE | Official Final Defense |  |  |  |  |  |  |  |  |  |  |  |  |  | ● |  |  |
| SUBMIT | Corrections, approval, hardbound copies and submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ● |

Master Thesis Gantt Chart

August 2026–May 2027

■ Writing   ■ Research / preparation   ■ Methodology / data   ■ Consultation / review   ■ Revision / integration   ■ Presentation / milestone

| PHASE | ACTIVITY | AUG 2026 | SEP | OCT | NOV | DEC | JAN 2027 | FEB | MAR | APR | MAY |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CH 1 | Chapter 1 drafting, consultation and freeze |  | ● |  |  |  |  |  |  |  |  |
| CH 2 | Literature search, synthesis, consultation and finalization |  |  | ● |  |  |  |  |  |  |  |
| CH 3 | Method design, drafting, consultation and integration |  |  | ● |  |  |  |  |  |  |  |
| OUTLINE | Slides, mock defense and official Outline Defense |  |  |  | ● |  |  |  |  |  |  |
| REVISION | Outline action report, corrections and protocol setup |  |  |  |  |  | ● |  |  |  |  |
| DATA | Satellite, OSM and boundary acquisition |  |  |  |  |  |  |  |  |  |  |
| DATA | Satellite preprocessing and road-graph preparation |  |  |  |  |  |  | ● |  |  |  |
| FEATURE | Environmental/road features and attributed graph |  |  |  |  |  |  | ● |  |  |  |
| DESIGN | Protected data splits and leakage controls |  |  |  |  |  |  | ● |  |  |  |
| MODEL | Random Forest, Spatial GCN and topology ablations |  |  |  |  |  |  |  | ● |  |  |
| OUTPUT | Project output / dashboard development and testing |  |  |  |  |  |  |  | ● |  |  |
| RESULTS | Evaluation, error analysis and spatial SUHI maps |  |  |  |  |  |  |  | ● |  |  |
| WRITE | Chapters 4–5 and complete manuscript |  |  |  |  |  |  |  | ● |  |  |
| FINAL | Adviser endorsement, panel package and mock defense |  |  |  |  |  |  |  |  |  |  |
| FINAL | Official Final Defense |  |  |  |  |  |  |  |  | ● |  |
| SUBMIT | Final action report, revisions, approval and hardbound copies |  |  |  |  |  |  |  |  |  | ● |

First-Semester Weekly Deliverables and Checkpoints

| WEEK | DATES | PRIMARY FOCUS | EXPECTED DELIVERABLE / CHECKPOINT |
| --- | --- | --- | --- |
| W1 | 24–30 Aug | Chapter 1 core writing | Complete background, problem, objectives, significance, and scope first draft. |
| W2 | 31 Aug–6 Sep | Chapter 1 completion and team review | Produce a clean Chapter 1 consultation copy; log unresolved questions and source gaps. |
| W3 | 7–13 Sep | Chapter 1 consultation; begin Chapter 2 search | Receive adviser feedback, assign revisions, and establish the literature-search and evidence-mapping plan. |
| W4 | 14–20 Sep | Freeze Chapter 1; build Chapter 2 | Close major Chapter 1 comments; complete literature screening, thematic outline, and conceptual-framework draft. |
| W5 | 21–27 Sep | Chapter 2 draft and consultation | Submit a coherent synthesis draft with verified references; capture adviser comments by theme. |
| W6 | 28 Sep–4 Oct | Chapter 2 revision; start Chapter 3 design | Resolve Chapter 2 comments; confirm datasets, variables, preprocessing, target definition, and evaluation strategy. |
| W7 | 5–11 Oct | Finalize Chapter 2; outline Chapter 3 | Complete reference audit and Chapter 2 sign-off; prepare the end-to-end methodology outline and task ownership. |
| W8 | 12–18 Oct | Chapter 3 preparation and drafting | Write data collection, preprocessing, feature construction, model development, evaluation, ethics, and limitations. |
| W9 | 19–25 Oct | Chapter 3 consultation / presentation | Present the methodology flow; record decisions on SUHI baseline, temporal alignment, buffers, edge weights, and data splits. |
| W10 | 26 Oct–1 Nov | Chapter 3 revision and full integration | Complete all three chapters, cross-check terminology and objectives, format citations, and secure adviser clearance. |
| W11 | 2–8 Nov | Final proposal presentation / defense | Freeze manuscript and slides, rehearse speaking roles and Q&A, present, and document panel/adviser action items. |
| W12 | 9–15 Nov | Corrections and contingency | Apply required corrections, finalize the revision matrix, and archive the approved manuscript and supporting files. |

Second-Semester Execution Plan

January–May 2027

| # | TARGET WEEKS | PRIMARY FOCUS | EXPECTED DELIVERABLE / CHECKPOINT |
| --- | --- | --- | --- |
| 1 | Jan W1–W2 | Protocol and corrections | Close Outline Defense comments; decide LST versus SUHI target, reference baseline, observation unit, sensor versions, temporal matching, buffers, edge weights, evaluation metric, and member ownership. |
| 2 | Jan W1–W4 | Data inventory and acquisition | Catalogue Landsat 8/9 Level-2, ECOSTRESS Level-2, OSM road data and the Davao boundary with product IDs, dates/times, versions, cloud cover and checksums. |
| 3 | Jan W3–Feb W2 | Satellite preprocessing | Apply product scale factors and QA masks; remove cloud, shadow, fill and uncertain pixels; clip, reproject and align rasters while preserving acquisition time and valid-pixel coverage. |
| 4 | Jan W3–Feb W2 | Road-graph preparation | Record OSMnx settings; simplify the drive network, consolidate genuine intersections, review components, project coordinates and audit missing road metadata. |
| 5 | Feb W1–W3 | Feature engineering | Compute LST/SUHI, NDVI and NDBI; test justified node buffers; summarize valid pixels; attach environmental and road attributes; document every imputation. |
| 6 | Feb W2–W3 | Experimental design | Freeze spatial blocks and any temporal holdout; separate training, validation and test data; mask target labels and check overlapping-pixel or neighboring-node leakage. |
| 7 | Feb W3–Mar W1 | Random Forest baseline | Train and tune RF using approved tabular predictors; save seeds, hyperparameters, feature importance, validation predictions and timing. |
| 8 | Feb W4–Mar W2 | Spatial GCN and ablations | Train the GCN on the frozen graph; tune on validation data only; compare real topology with no-edge or shuffled-edge controls; monitor overfitting and oversmoothing. |
| 9 | Feb W3–Mar W3 | Project output | Build and test the required software, website or dashboard; connect approved results; include map legends, limitations, reproducible exports and user documentation. |
| 10 | Mar W2–W3 | Evaluation and mapping | Evaluate the untouched test set with RMSE, MAE and R²; compare models, inspect residuals and uncertainty, and produce defensible LST/SUHI maps. |
| 11 | Mar W1–W4 | Chapters 4–5 and archive | Write results, discussion, conclusions and recommendations; integrate Chapters 1–5; freeze scripts, versions, seeds, data dictionary, logs and rerun instructions. |
| 12 | Mar W3–Apr W1 | Adviser review and endorsement | Submit the final manuscript, project output and accomplished Outline Defense Action Taken Report; resolve adviser comments and obtain endorsement. |
| 13 | Mar W4–Apr W1 | Defense package and rehearsal | Give printed and electronic copies to panel members at least three days before defense; freeze slides, assign speaking roles and conduct technical Q&A rehearsals. |
| 14 | Apr W2 | Official Final Defense | Present the complete study and project output; demonstrate that model comparisons use the same protected data; record every panel action item and assigned owner. |
| 15 | Apr W2–May | Corrections and submission | Submit the Final Defense Action Taken Report and revised manuscript within 15 days; complete proofreading, panel approval, two hardbound copies and Dean's Office submission. |